## Project Details
TEAM ORBIT – LITMUS AI STARTUP IDEA VALIDATOR
Team Members | Lithen Deep Gowda; Nandhini K; Kalavath Kamali; MANASA C A; Ashmitha Shivarathri
Project | AI Based Startup Idea Validator with Market Analysis Assistance
Milestone | Milestone 2 / Sprint 2
Live Site | https://orbit-isb-7-0.vercel.app
Backend | https://orbit-isb-7-0-staging.onrender.com
API Documentation | https://orbit-isb-7-0-staging.onrender.com/docs
GitHub Repository | https://github.com/lithendeepjersey7-lab/orbit-ISB-7.0
Main Flow | Idea Input → Web Search → Market Analysis → Competitor Analysis → SWOT/Risk → MVP Recommendation → Final Validation Report
Frontend | React / Vercel
Backend | FastAPI / Render
AI & Search | Gemini + LangGraph + Tavily

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 2 | Sprint 2 | US-01 | Validate a startup idea entered in 2–3 lines and generate a structured validation request | Must | — | Lithen Deep Gowda | Done
Sprint 2 | Sprint 2 | US-02 | Generate market analysis covering market size, opportunity, trends and supporting evidence | Must | US-01 | Nandhini K | Done
Sprint 2 | Sprint 2 | US-03 | Identify relevant competitors and present a structured competitor comparison | Must | US-01 | MANASA C A | Done
Sprint 2 | Sprint 2 | US-04 | Perform SWOT and risk analysis to identify strengths, weaknesses, opportunities and threats | Must | US-01 | Ashmitha Shivarathri | Done
Sprint 2 | Sprint 2 | US-05 | Recommend an MVP scope based on the validated idea, market findings and risks | Must | US-02, US-04 | Kalavath Kamali | Done
Sprint 2 | Sprint 2 | US-06 | Combine agent outputs into a clear startup validation report | Must | US-02, US-03, US-04, US-05 | Lithen Deep Gowda | Done
Sprint 2 | Sprint 2 | US-07 | Integrate Web Search, Market, Competitor, SWOT/Risk and MVP analysis into the backend workflow | Must | US-01 | Nandhini K | Done
Sprint 2 | Sprint 2 | US-08 | Connect frontend forms and result pages with backend APIs for end-to-end validation | Must | US-06, US-07 | MANASA C A | Done
Sprint 2 | Sprint 2 | US-09 | Add validation, error handling and reliable empty-result behaviour for analysis requests | Should | US-07 | Ashmitha Shivarathri | Done
Sprint 2 | Sprint 2 | US-10 | Deploy and verify the application using Vercel frontend, Render backend and API documentation | Should | US-08, US-09 | Kalavath Kamali | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours ¦ Team Orbit – Litmus AI Startup Idea Validator
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 83 | 30 | 31 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-01 | T201 | Connect startup-idea input form and validate request payload | 01-Sep-2026 | 02-Sep-2026 | Lithen Deep Gowda | Frontend / Integration | Done | 6 | Day 1: 3; Day 2: 3
US-02 | T202 | Implement market analysis agent and structured market-result schema | 01-Sep-2026 | 03-Sep-2026 | Nandhini K | AI / Backend | Done | 10 | Day 1: 4; Day 2: 4; Day 3: 2
US-03 | T203 | Implement competitor discovery and comparison output | 02-Sep-2026 | 04-Sep-2026 | MANASA C A | AI / Backend | Done | 9 | Day 1: 3; Day 2: 4; Day 3: 2
US-04 | T204 | Implement SWOT and risk analysis workflow | 03-Sep-2026 | 05-Sep-2026 | Ashmitha Shivarathri | AI / Backend | Done | 8 | Day 1: 4; Day 2: 2; Day 3: 2
US-05 | T205 | Implement MVP recommendation logic from analysis results | 04-Sep-2026 | 06-Sep-2026 | Kalavath Kamali | AI / Product | Done | 7 | Day 1: 3; Day 2: 2; Day 3: 2
US-06 | T206 | Integrate all agent outputs into final validation report | 05-Sep-2026 | 07-Sep-2026 | Lithen Deep Gowda | Backend / Integration | Done | 10 | Day 1: 3; Day 2: 4; Day 3: 3
US-07 | T207 | Connect backend agent workflow and API endpoints | 02-Sep-2026 | 07-Sep-2026 | Nandhini K | Backend | Done | 10 | Day 1: 3; Day 2: 3; Day 3: 2; Day 4: 2
US-08 | T208 | Integrate React frontend with validation APIs and result views | 06-Sep-2026 | 08-Sep-2026 | MANASA C A | Frontend | Done | 8 | Day 1: 2; Day 2: 3; Day 3: 3
US-09 | T209 | Add validation, exception handling and empty-result checks | 07-Sep-2026 | 09-Sep-2026 | Ashmitha Shivarathri | Testing / QA | Done | 7 | Day 1: 2; Day 2: 3; Day 3: 2
US-10 | T210 | Deploy, smoke-test and verify frontend, backend and API docs | 08-Sep-2026 | 10-Sep-2026 | Kalavath Kamali | Deployment / QA | Done | 8 | Day 1: 3; Day 2: 3; Day 3: 2
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 1 | Aligning idea-input and validation workflow | Finalized 2–3 line idea input, validation flow and team task ownership.
Sprint 2 | Day 2 | Market analysis output structure | Defined structured market-analysis fields and connected evidence-based search.
Sprint 2 | Day 3 | Competitor data consistency | Standardized competitor records and comparison fields.
Sprint 2 | Day 4 | SWOT/risk response formatting | Integrated SWOT and risk output into the common analysis schema.
Sprint 2 | Day 5 | MVP recommendation dependencies | Mapped market and risk findings into MVP recommendation inputs.
Sprint 2 | Day 6 | Multiple-agent integration | Combined Web Search, Market, Competitor, SWOT/Risk and MVP workflows.
Sprint 2 | Day 7 | Frontend-backend API integration | Connected React screens with backend validation endpoints and handled API responses.
Sprint 2 | Day 8 | Report presentation consistency | Improved result sections and made the final validation report easier to read.
Sprint 2 | Day 9 | Error and empty-result handling | Added validation and safe handling for incomplete or unavailable analysis results.
Sprint 2 | Day 10 | Deployment verification | Verified Vercel frontend, Render backend and API documentation; completed milestone smoke testing.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 2 | 01-Sep-2026 | 10-Sep-2026 | Lithen Deep Gowda | Start documenting integration decisions while developing the agent workflow. | Stop postponing integration testing until the end of the sprint. | Continue backend modularization and team code reviews. | Completed backend workflow integration and supported deployment verification.
2 | Sprint 2 | 01-Sep-2026 | 10-Sep-2026 | Nandhini K | Start defining API response schemas before implementing dependent agents. | Stop changing response structures without communicating dependencies. | Continue AI workflow development and technical documentation. | Standardized agent outputs and connected the market-analysis workflow.
3 | Sprint 2 | 01-Sep-2026 | 10-Sep-2026 | Kalavath Kamali | Start validating UI behaviour with real backend responses earlier. | Stop relying only on mock data during UI checks. | Continue reusable React components and clean result presentation. | Integrated validation results into the frontend and improved report readability.
4 | Sprint 2 | 01-Sep-2026 | 10-Sep-2026 | MANASA C A | Start regression testing whenever a major agent/API is integrated. | Stop treating QA as only a final-stage activity. | Continue end-to-end testing and deployment checks. | Verified API-to-frontend flow and tested common validation scenarios.
5 | Sprint 2 | 01-Sep-2026 | 10-Sep-2026 | Ashmitha Shivarathri | Start tracking edge cases such as empty or incomplete search results. | Stop assuming every external search will return complete evidence. | Continue structured testing, issue tracking and documentation. | Added validation/error handling and verified safe behaviour for edge cases.